## CAS ERP
Implementation Plan for CAS and ERP System with Sales Data Transfer
Target Date | Date Finish | Topic | Responsible | Supported by | Remarks
July 6,2023 | July 6,2023 | Arrange Meeting with Supplier for CAS / ERP Supplier | Darwin B. | Bryan | Done
July 7,2023 | July 7,2023 | Send the Presentation file of CAS / ERP together with Quotation and Price Comparison | Darwin B. | Sir Martin / Sir Boge | Done
July 8,2023 | July 8,2023 | CAS / ERP Discussion for the BPTI System Flow | Darwin B. | Bryan
|  | Sales Module Discussion | Darwin B. | Bryan | Done
July 10,2023 | July 10,2023 | Purchasing Module | Darwin B. | Bryan | Done
|  | Engineering Module | Darwin B. | Bryan | Done
July 11,2023 | July 11,2023 | Planning Module | Darwin B. | Bryan | Done
|  | Manufacturing module | Darwin B. | Bryan | Done
July 12,2023 | July 12,2023 | Warehouse Module | Darwin B. | Bryan | Done
|  | MES System Designing | Darwin B. | Bryan | Done
July 14,2023 | July 28,2023 | Approval of Top Management for CAS/ERP System | Darwin B. | Bryan | Done
|  | Making of Advance Payment for Downpayment | Darwin B. | Bryan | Done
July 17,2023 | August 8,2023 | System Requirement Study with Supplier | Darwin B. | Bryan | Done
July 19,2023 |  | Implementation and Testing | Bryan |  | On Going
September 4-9, 2023 |  | End User Training | Bryan |  | On Going
September 11-16, 2023 |  | Parallel System Testing | Bryan
September 18-23, 2023 |  | Uploading of System Balances | Supplier
September 25-30, 2023 |  | Checking of Uploaded Balances and PC Testing | Supplier
October 2,2023 |  | System GO Live | Bryan & BPTI Team | BPTI Team