## 1st Week
Implementation Plan for CAS and ERP System with Sales Data Transfer
Date | Topic | Responsible | Supported by | Remarks
July 6,2023 | Arrange Meeting with Supplier for CAS / ERP Supplier | Darwin B. | Bryan | Done
July 7,2023 | Send the Presentation file of CAS / ERP together with Quotation and Price Comparison | Darwin B. | Sir Martin / Sir Boge | Done
July 8,2023 | CAS / ERP Discussion for the BPTI System Flow | Darwin B. | Bryan
| Sales Module Discussion | Darwin B. | Bryan
July 10,2023 | Purchasing Module | Darwin B. | Bryan
| Engineering Module | Darwin B. | Bryan
July 11,2023 | Planning Module | Darwin B. | Bryan
| Manufacturing module | Darwin B. | Bryan
July 12,2023 | Warehouse Module | Darwin B. | Bryan
| MES System Designing | Darwin B. | Bryan
July 14,2023 | Approval of Top Management for CAS/ERP System | Darwin B. | Bryan
| Making of Advance Payment for Downpayment | Darwin B. | Bryan
July 17,2023 | System Requirement Study with Supplier | Darwin B. | Bryan
July 19,2023 | Implementation and Testing | Darwin B. | Bryan
July 24- Aug 4,2023 | End User Training | Darwin B. | Bryan
July 25- Aug 28,2023 | Parallel System Testing | Darwin B. | Bryan
August 28-29, 2023 | Uploading of System Balances | Supplier | Bryan
August 30-31, 2023 | Checking of Uploaded Balances and PC Testing | Supplier | Bryan
September 1,2023 | System GO Live | Bryan & BPTI Team | BPTI Team